## Overview
Firewall change and rollback record
HAI Consulting ¦ Secure IT by design
About this template | Plan, approve, test, and close a firewall change with the business reason and rollback path in one record.
Intended use | Intended for Network administrators, security teams, service owners, change managers, and managed service providers. Typical completion time: 15 to 30 minutes for a routine change; longer for complex or high-risk work.
Before you start | • Create one record per logically related change. Link related records rather than combining unrelated rules.
• Use the organization's standard change identifier and time zone.
• Write source, destination, service, direction, and action explicitly. Avoid broad terms such as any unless there is a documented reason.
• Do not paste passwords, private keys, pre-shared keys, tokens, or unredacted secrets into the record.
• Obtain approval before implementation. Record an emergency change as emergency, with retrospective review requirements.
• Close the record only after validation, monitoring, documentation updates, and evidence capture are complete.
Completing this workbook | Work through the numbered tabs in order. Shaded cells are guidance and are locked; the blank entry cells are yours to complete. Sheet protection is applied without a password, so you can unprotect any sheet if you need to restructure it.
Do not record | Do not paste passwords, private keys, pre-shared keys, API tokens or unredacted secrets into this workbook. Reference where a credential is held instead of copying its value.
Source | https://hai.consulting/resources/firewall-change-plan-template
This template is general guidance. Adapt it to your environment, change controls and legal requirements before operational use.

## 1. Change identification
1. Change identification
Firewall change and rollback record
Item | Your entry | Guidance
FIELDS
Change ID * |  | Unique ticket or change number Free text Required
Title * |  | Short description of the intended network access Free text Required
Requester * |  | Name, team, and contact Free text Required
Business or service owner * |  | Person accountable for the service need Free text Required
Technical implementer * |  | Person or provider making the change Free text Required
Firewall or policy domain * |  | Device, cluster, cloud policy, tenant, or management domain Free text Required
Environment * |  | Choose from list Required
Change class * |  | Choose from list Required
Planned window * |  | Include date, start, end, and time zone Start and end (YYYY-MM-DD HH:MM) Required
Related incident, problem, project, or vendor ticket |  | References only; do not include secrets Free text

## 2. Business reason and expiry
2. Business reason and expiry
Firewall change and rollback record
Item | Your entry | Guidance
FIELDS
Business requirement * |  | Who needs to communicate, for what service, and why? Free text (multi-line) Required
Consequence if not implemented * |  | Operational impact, deadline, and affected users or service Free text (multi-line) Required
Permanent or temporary * |  | Choose from list Required
Expiry date and time |  | Required for temporary access Date and time (YYYY-MM-DD HH:MM)
Review date * |  | When the continuing need will be confirmed Date (YYYY-MM-DD) Required
Rule owner * |  | Named role responsible for future review Free text Required

## 3. Technical specification
3. Technical specification
Firewall change and rollback record
Item | Your entry | Guidance
REPEATABLE GROUP
One row per rule or object change
FIELDS
Sequence * |  | Number Required
Source zone or interface * |  | Free text Required
Source address, object, or group * |  | Free text Required
Destination zone or interface * |  | Free text Required
Destination address, object, or group * |  | Free text Required
Protocol and destination port or application * |  | Free text Required
Direction * |  | Choose from list Required
Action * |  | Choose from list Required
NAT requirement * |  | None, source NAT, destination NAT, or exact requirement Free text Required
Logging * |  | Start, end, deny, session, or platform-specific setting Free text Required
Security profile or inspection |  | Free text
Rule position and interaction * |  | Placement, shadowing, overlap, implicit rules, and policy route effects Free text (multi-line) Required
Rule comment * |  | Include change ID, owner, purpose, and expiry where supported Free text Required

## 4. Risk and dependency review
4. Risk and dependency review
Firewall change and rollback record
Item | Your entry | Guidance
CHECKLIST
Source and destination are as narrow as the requirement permits.
Ports, protocols, and applications are as narrow as the requirement permits.
The rule does not unintentionally expose management interfaces.
Internet exposure and egress implications have been reviewed.
NAT, routing, VPN, DNS, load balancer, proxy, and cloud security-policy dependencies have been checked as applicable.
Existing rules were checked for duplication, overlap, shadowing, or conflict.
Logging and retention are suitable for validation and investigation.
Required inspection profiles and exceptions are documented.
High availability or configuration synchronization has been considered.
A temporary rule has an expiry mechanism or scheduled removal task.
FIELDS
Risk if implemented * |  | Free text (multi-line) Required
Risk rating and method * |  | Use the organization's rating scheme Free text Required
Compensating controls |  | Free text (multi-line)
Known dependencies * |  | Free text (multi-line) Required
Affected monitoring or detection |  | Free text (multi-line)

## 5. Test and implementation plan
5. Test and implementation plan
Firewall change and rollback record
Item | Your entry | Guidance
FIELDS
Pre-change checks * |  | Health, backup/export, sessions, synchronization, monitoring, and baseline evidence Free text (multi-line) Required
Implementation steps * |  | Exact, reviewable sequence; reference approved scripts or platform commands securely Numbered list, one item per line Required
Expected result * |  | Free text (multi-line) Required
Positive test * |  | Authorized traffic that should succeed Free text (multi-line) Required
Negative test * |  | Traffic that should remain blocked Free text (multi-line) Required
Monitoring during and after change * |  | Free text (multi-line) Required
Validation owner * |  | Free text Required
Observation period * |  | Duration (e.g. 2h 30m) Required

## 6. Rollback and stop conditions
6. Rollback and stop conditions
Firewall change and rollback record
Item | Your entry | Guidance
FIELDS
Rollback trigger * |  | Specific failed tests, errors, performance conditions, or elapsed-time threshold Free text (multi-line) Required
Point of no return * |  | State none if the change remains fully reversible Free text Required
Rollback steps * |  | Numbered list, one item per line Required
Estimated rollback time * |  | Duration (e.g. 2h 30m) Required
Rollback decision authority * |  | Free text Required
Post-rollback validation * |  | Free text (multi-line) Required

## 7. Approval and closeout
7. Approval and closeout
Firewall change and rollback record
Item | Your entry | Guidance
APPROVAL ROLES
Service owner
Security or technical reviewer
Change authority
Implementer acknowledgement
CLOSEOUT FIELDS
Actual start and end time with time zone
Implementation result: successful, partially successful, rolled back, or failed
Test evidence references
Observed errors or unexpected effects
Rollback performed and reason
Monitoring result
Documentation, diagram, inventory, and rule-register updates
Temporary-rule removal task
Follow-up actions with owner and due date
Final reviewer and closure date

## Important limitations
Important limitations
Firewall change and rollback record
For general operational use only. These materials are not legal advice, compliance advice, a warranty, or a complete control framework. Using a template does not establish that a change, assessment, incident plan, or recovery capability is adequate. Obtain appropriate technical, legal, privacy, insurance, and regulatory advice for your circumstances.
Item | Your entry | Guidance
This template does not authorize a firewall change. Follow your organization's access, change, security, privacy, and vendor procedures.
Do not place passwords, private keys, recovery codes, sensitive personal information, or unredacted secrets in forms, worksheets, tickets, or email. Use an approved secure channel for confidential material.
Resource version 1.0. Suggested download filename: hai-firewall-change-template.html.