## Overview
Service recovery test plan and evidence record
HAI Consulting ¦ Secure IT by design
About this template | Test whether a service can be restored under defined conditions, with safe boundaries, timestamps, acceptance criteria, and follow-up actions.
Intended use | Intended for Service owners, infrastructure and cloud teams, application owners, backup administrators, continuity planners, security teams, and vendors. Typical completion time: Planning time varies by service; reserve enough time for safe teardown, evidence capture, and review.
Before you start | • Test a service outcome, not only a backup job or single-file restore.
• Define the test boundary, assumptions, recovery point, recovery time, dependencies, and acceptance criteria before execution.
• Use an isolated environment unless production testing has separate, explicit approval.
• Use authorized and appropriately protected test data. Mask or synthesize personal and confidential information where feasible.
• Record actual timestamps and errors as they occur. Do not rewrite the log to make the test appear cleaner.
• Treat a partially successful test as evidence: document the limit, risk, owner, and retest condition.
Completing this workbook | Work through the numbered tabs in order. Shaded cells are guidance and are locked; the blank entry cells are yours to complete. Sheet protection is applied without a password, so you can unprotect any sheet if you need to restructure it.
Do not record | Do not paste passwords, private keys, pre-shared keys, API tokens or unredacted secrets into this workbook. Reference where a credential is held instead of copying its value.
Source | https://hai.consulting/resources/recovery-test-template
This template is general guidance. Adapt it to your environment, change controls and legal requirements before operational use.

## 1. Test identity and authorizat
1. Test identity and authorization
Service recovery test plan and evidence record
Item | Your entry | Guidance
FIELDS
Test ID and title
Service name and business owner
Technical owner and test lead
Participants and responsibilities
Approved date, start, end, and time zone
Environment and location
Related continuity, disaster recovery, change, risk, or vendor records
Approvers for execution, access, data use, network isolation, and teardown
Escalation contact and method

## 2. Objective, scope, and succes
2. Objective, scope, and success
Service recovery test plan and evidence record
Item | Your entry | Guidance
FIELDS
Business capability to be recovered
Reason for the test
In-scope components, data, locations, identities, networks, and providers
Out-of-scope items
Failure scenario or recovery assumption
Recovery time objective, source, and business owner
Recovery point objective or acceptable data loss, source, and business owner
Maximum tolerable outage or other business limit, if defined
Test start event and recovery-time clock rule
Recovery point selected for the test
Functional, security, data-integrity, performance, and business acceptance criteria
Known limitations that prevent a full test

## 3. Dependency and readiness che
3. Dependency and readiness check
Service recovery test plan and evidence record
Item | Your entry | Guidance
DEPENDENCY CATEGORIES
Facilities, power, environmental systems, and physical access
Compute, virtualization, containers, storage, and cloud subscriptions
Network routing, switching, firewall, DNS, DHCP, VPN, proxies, load balancers, and internet connectivity
Identity, directory, privileged access, MFA, service accounts, secrets, keys, and certificates
Operating systems, middleware, databases, applications, integrations, queues, and scheduled jobs
Backup catalogues, repositories, media, immutability or offline copies, and encryption-key access
Monitoring, logging, security tooling, time synchronization, and alerting
Third parties, licensing, support contracts, telecom, and vendor access
People, contact paths, documentation, scripts, equipment, and replacement capacity
READINESS CHECKLIST
The backup or recovery source has been identified and its integrity checks reviewed.
Required versions, installers, images, licences, keys, certificates, and configuration exports are available.
Recovery credentials were tested without exposing them in the test record.
The dependency order and responsible owner for each step are documented.
The target environment has enough capacity and appropriate network isolation.
Production routes, DNS, email, jobs, integrations, monitoring, and automation cannot accidentally target the recovered test system.
Test data handling and disposal have approval.
Observers know the stop conditions and escalation path.
Baseline production health and backup evidence were captured where relevant.
Teardown and secure disposal steps are assigned.

## 4. Safety, stop conditions, and
4. Safety, stop conditions, and rollback
Service recovery test plan and evidence record
Item | Your entry | Guidance
FIELDS
Potential production, security, privacy, cost, licensing, and vendor impacts
Controls that keep the test isolated
Prohibited actions
Stop conditions, including unexpected production communication, data exposure, capacity pressure, or loss of control
Person authorized to stop the test
Containment or rollback steps
Method to verify that production was not changed
Emergency contacts
Teardown and data-destruction method
Evidence required to confirm cleanup

## 5. Recovery procedure
5. Recovery procedure
Service recovery test plan and evidence record
Item | Your entry | Guidance
REPEATABLE COLUMNS
Step
Component or dependency
Procedure reference
Expected duration
Owner
Prerequisite
Expected result
Validation method
Rollback or alternate path
REQUIRED MILESTONES
Incident or outage assumption declared
Recovery decision authorized
Recovery environment available
Identity and privileged access usable
Network and name services usable
Data restored to the selected recovery point
Application components restored in dependency order
Integrations reconnected or safely simulated
Security controls, logging, monitoring, and backup protection restored
Technical validation complete
Business-owner validation complete
Return-to-service decision recorded
Test environment isolated and removed or retained under approval

## 6. Timestamped execution log
6. Timestamped execution log
Service recovery test plan and evidence record
Item | Your entry | Guidance
REPEATABLE COLUMNS
Sequence
Actual timestamp and time zone
Elapsed time
Actor
Action or decision
Observed result
Evidence ID
Error or variance
Workaround
Approver if required
EVIDENCE EXAMPLES
System and application status
configuration export
backup catalogue reference
restore job log
hash or integrity check where appropriate
authentication test
network test
application transaction
monitoring event
business-owner acceptance

## 7. Validation record
7. Validation record
Service recovery test plan and evidence record
Item | Your entry | Guidance
TEST GROUPS
Data |  | – Selected recovery point is supported by evidence. – Record counts, sample transactions, or application-level checks meet agreed criteria. – Data is readable, consistent, and protected appropriately.
Function |  | – Authorized users can authenticate. – Critical business workflows complete. – Required integrations work or approved simulations pass. – Scheduled or automated activity behaves safely.
Security |  | – Privileged access is restricted. – Certificates, keys, and secrets are correct and protected. – Required firewall, endpoint, hardening, logging, monitoring, and backup controls are active. – Temporary test access is identified for removal.
Operations |  | – Alerts, logs, support access, documentation, and ownership are in place. – Capacity and performance meet the agreed test threshold. – The team can perform the next backup and planned operational task.
Business acceptance |  | – The business owner completed the agreed acceptance procedure. – Unmet criteria and residual risk are recorded. – The return-to-service or test-completion decision has a named approver and time.

## 8. Results and objectives
8. Results and objectives
Service recovery test plan and evidence record
Item | Your entry | Guidance
FIELDS
Overall result: met, partly met, not met, or test aborted
Actual recovery point achieved and calculation method
Actual recovery time achieved and clock endpoints
Criteria passed, failed, or not tested
Assumptions that held and assumptions that failed
Manual workarounds used
Production impact, if any
Evidence limitations
Decision on whether the result supports the stated objective
Business owner, technical owner, and test lead sign-off

## 9. Improvement and retest regis
9. Improvement and retest register
Service recovery test plan and evidence record
Item | Your entry | Guidance
REPEATABLE COLUMNS
Action ID
Observation or failed criterion
Risk or consequence
Corrective action
Owner
Priority
Target date
Dependency
Interim control
Closure evidence
Retest required
Retest date
Status
AFTER ACTION QUESTIONS
Which step consumed more time than expected, and why?
Which credentials, tools, files, contacts, or approvals were hard to obtain?
Where did the documented sequence differ from reality?
Which dependencies were missing or misunderstood?
Did any test control nearly allow production impact or data exposure?
What should be changed in the runbook, architecture, backup design, monitoring, staffing, or service objective?
What must be fixed before the next test, and what can be accepted with approval?

## Important limitations
Important limitations
Service recovery test plan and evidence record
For general operational use only. These materials are not legal advice, compliance advice, a warranty, or a complete control framework. Using a template does not establish that a change, assessment, incident plan, or recovery capability is adequate. Obtain appropriate technical, legal, privacy, insurance, and regulatory advice for your circumstances.
Item | Your entry | Guidance
A successful test supports only the service boundary, recovery point, conditions, evidence, and date recorded. It does not guarantee recovery in a different incident or prove that every dependency is resilient.
Do not place passwords, private keys, recovery codes, sensitive personal information, or unredacted secrets in forms, worksheets, tickets, or email. Use an approved secure channel for confidential material.
Resource version 1.0. Suggested download filename: hai-recovery-test-template.html.